## Roadmap
item | status | remarks
1) Select Project | Done | Apple recognition
2) Select Dataset | Done | Kaggle dataset
3) Agree methods/tools | Doing | (i) Use Python with keras/tensor flow; (ii) CVAC;
4) Send materials on Basic elements of ML and coding examples | Doing | (i) Dive into deep learning; (point elements) (ii) Project examples by Alexandru
5) Project developent | TODO | Naive approach
Image pre-processing
Image labelling
Object recognition
Object recognition
Final report

## Project steps
Date | Event
04.09.2023 | Image pre-processing fundamentals Keras fundamentals (image loading) Send materials for studying
11.09.2023 | Keras training/tests
18.09.2023 | Keras model hyperparameters
25.09.2023 | Object recognition and detection
30.09.2023 | Final report

## Project steps 2
Week | Date | Stage | Topic | Event | Homerowk | Remarks
1 | 2023-09-06 | Preparation | 1 | (i) PACE Framework (Alexandr) (ii) Discuss about the machine learning cycle (Pedro) (ii) Fundamentals of image loading with OpenCV: image loading, data appending, visualize (Alexandr); | Homework, example use cv2 to import , visualize pictures via matplotlib , change color scheme, check few parameters of "imread" method Essentially use cv2 (opencv) to import data;
1 | 2023-09-08 | Analyze | 2 | (i) Logical filterings, masking, threshholding (Pedro); (ii) brightness, blurring, input noise (Pedro); (ii) changing background + masking (Alexandr) | Homework in a form of masking (Thresholding, isolating specific color, blacken specific areas of pictures based on RGB values, essentially how to apply logical filtering over 3 dim array);
2 | 2023-09-13 | Analyze | 3.1 & 3.2 | (i) Image selection and pre-processing: resizing, padding, normalization (Pedro); (ii) Data augmentation (Alexandr), | (i) Apply cv2 methods like cv2.resize , cv2.copyMakeBorder(), generate crops of images; (ii)Try interpolation methods for resizing; (iii) Select picture with target and implement image processing over it;
2 | 2023-09-15 | Construct | 4 | (i) Splitting data into Train ,Test, Validation Sets and Setting Baseline Model and Baselie Accuracy, f1, recall , precision (Binary Forecast for Image Recognition)
|  | Construct | 5 | (i) Set Up CNN Architecture(model_v0) and Train Model for Image Recognition; (ii) Compare perfomance against Baseline
|  | Construct | 6 | (i) Set Up cv2.ximgproc.segmentation.createSelectiveSearchSegmentation() class (ss1) and generate proposals ( sub pics, rectangulars, rects ). (ii) Use original picture with multiple apples
|  | Construct | 7 | (i) Set Up cv2.ximgproc.segmentation.createSelectiveSearchSegmentation() class (ss2) and generate proposals ( sub pics ); (ii) Use preprocessed original picture with threshold over all colors combinations except red ones;
3 | 2023-09-20 | Construct | 8 | (i) Binary Forecast for Image Detection using model_v0 (ii) Apply model_v0 over ss1 to predict if proposal contains Apple (iii) Apply model_v0 over ss2 to predict if proposal contains Apple (iv) Compare perfomance and select either ss1 or ss2 proposals (v) Does Thresholding benefits Accuracy and Running Time?
|  | Construct | 9 | (i) Write IoU python function to apply over rectangles which contains apples (prediction based on ss1 or ss2)
|  | Construct | 10 | (i) Write Non maximum suppression python function and apply to estimate apples counts over original pucture (function unites similar proposals into 1) https://towardsdatascience.com/non-maximum-suppression-nms-93ce178e177c
|  | Construct | 11 | Select 10 or more pictures with multiple apples , count its numbers , feed photos to the pipeline and compare accuracy of model_v0 predictions over actual counts, we would require accuracy only | Homework 4, steps 1 - 11 Analyze , Constuct and Execute Stage We seek to achive accuray of image detection of more than 70%
3 | 2023-09-22 | Execute | 12 | Repeat Steps from 1 to 11 over updated Dataset (more pictures, different preprocessing, more or less augmented data, different model_v0 architecture)
4 | 2023-09-27 | Execute | 12 | Repeat Steps from 1 to 11 over updated Dataset (more pictures, different preprocessing, more or less augmented data, different model_v0 architecture)
4 | 2023-09-29 | Review | 13 | Review results

## Main Steps
1) Learn Data Science PACE and CRISP framework
2) Learn image processing with cv2 methods and logical filtering
3) Learn Keras Sequential class for Image Classification
4) Learn about cv2 classes and methods applied for Image Detection ( R-CNN, Region-Based Convolutional Neural Network )
5) Learn Concepts of IoU and Non Maximum Supression applied for Image Detection